## TestCases
1.Login Module
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC01 | Valid Login | Enter standard_user + secret_sauce | User should login successfully | User logged in and redirected to Products | PASS
TC02 | Invalid Password | Enter valid user + wrong password | Error message should display | "Username and password do not match" displayed | PASS
TC03 | Invalid Username | Enter wrong user + valid password | Error message should display | "Username and password do not match" displayed | PASS
TC04 | Empty Fields | Click login without data | Validation message should appear | "Username is required" displayed | PASS
TC05 | Password Masking | Type in password field | Password should be hidden (••••) | Password is encrypted/masked | PASS
TC06 | Locked Out User | Login with locked_out_user | Error message for locked user | "Sorry, this user has been locked out" displayed | PASS
TC07 | Logout | Click Sidebar -> Logout | Redirect to Login page | User successfully logged out | PASS
2. Product Page & Sorting
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC08 | Product Display | Login -> View products | All 6 items should be visible | Items are displayed with name & price | PASS
TC09 | Product Details | Click on "Sauce Labs Backpack" | Product detail page should open | Shown description and price of backpack | PASS
TC10 | Image Load | Check all product images | Images should load correctly | All product images are visible | PASS
TC11 | Sort: A to Z | Select Name (A to Z) | Alphabetical order | Products sorted A to Z | PASS
TC12 | Sort: Z to A | Select Name (Z to A) | Reverse alphabetical order | Products sorted Z to A | PASS
TC13 | Sort: Low to High | Select Price (low to high) | Sorted by lowest price first | Price starting from $7.99 | PASS
TC14 | Sort: High to Low | Select Price (high to low) | Sorted by highest price first | Price starting from $49.99 | PASS
3. Cart & Add to Cart
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC15 | Add to Cart | Click "Add to Cart" on any item | Item should be added instantly | "Add to Cart" changed to "Remove" | PASS
TC16 | Cart Icon Update | Add 2 products to cart | Cart count should show '2' | Cart bubble updated to 2 | PASS
TC17 | Remove from Cart | Click "Remove" button | Item should be removed | Cart count decreased/Item removed | PASS
TC18 | Persistence | Add item -> Logout -> Login | Item should remain in cart | Cart still has the added item | PASS
TC19 | Remove from Cart (Delayed) | Click Remove on 3 items | Instant removal | System took ~60 sec to update | FAIL
TC20 | Continue Shopping | Inside cart -> Click 'Continue' | Back to inventory page | Redirected to Products page | PASS
4. Checkout Process
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC21 | Checkout: Info | Fill details -> Click Continue | Move to Overview page | Redirected to step two (Overview) | PASS
TC22 | Empty Info | Leave Name empty -> Continue | Error: "First Name is required" | Error message displayed correctly | PASS
TC23 | Total Calculation | Add items -> Check Overview | Total = Item total + Tax | Calculation is 100% accurate | PASS
TC24 | Order Completion | Click "Finish" | Show "Thank You" message | Order dispatched message shown | PASS
TC25 | Cancel Checkout | Click "Cancel" on Info page | Back to Cart page | Redirected back to Cart successfully | PASS
5. Side Menu & Footer
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC26 | Reset App State | Add item -> Click Reset State | Cart should be cleared | Cart count became 0 instantly | PASS
TC27 | About Link | Click Menu -> About | Redirect to SauceLabs.com | Redirected to official site | PASS
TC28 | Sidebar Close | Open Menu -> Click 'X' | Menu should close | Sidebar closed successfully | PASS
TC29 | Twitter Link | Click Twitter icon in footer | Open official Twitter page | Twitter page opened in new tab | PASS
TC30 | Facebook Link | Click Facebook icon | Open official Facebook page | Facebook page opened in new tab | PASS
6. Negative & Performance (Edge Cases)
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC31 | Direct URL Access | Copy 'inventory' link -> Logout -> Paste | Access Denied/Redirect | Successfully redirected to Login | PASS
TC32 | Problem User UI | Login with problem_user | UI should be perfect | Images are broken/Incorrect icons | FAIL
TC33 | Glitch User Performance | Login with performance_glitch_user | Page should load fast | Significant delay in page loading | FAIL
TC34 | Invalid Zip Code | Enter 'ABC' in Zip Code | Should restrict/Error | Accepted alphabets in zip field | FAIL
TC35 | Back Button Logic | Logout -> Click Browser Back | Should not see private data | User could see cached dashboard | FAIL
7. Missing Features (Non-functional in Sauce Demo)
TC ID | Scenario | Steps | Expected Result | Actual Result | Status
TC36 | Referral Page | Click Referral button | Referral info should open | Feature not responding/Button dead | FAIL
TC37 | Blog Section | Click Blog button | Latest blogs should show | Page not found/Not responding | FAIL
TC38 | Wishlist Function | Click Wishlist icon | Save item for later | Feature not implemented | FAIL
TC39 | Search Feature | Type "Backpack" in search | Show matching results | No search bar available | FAIL
TC40 | User Profile Pic | Click on Profile icon | Upload/View profile pic | Feature not responding | FAIL

## BugReport
Bug ID | Related TC ID | Bug Title / Summary | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status
BG-01 | TC32 | Broken Images on Inventory Page | Medium | High | 1. Login with problem_user | Each product should have a unique image. | All products show the same "Dog" placeholder image. | Open
2. View product list.
BG-02 | TC33 | Login Response Latency (5s+) | Low | Medium | 1. Use performance_glitch_user | Redirect to Products should be < 1 sec. | Loading spinner/hang for ~5.3 seconds before redirect. | Open
2. Click 'Login'.
BG-03 | TC39 | Referral Button Unresponsive | High | High | 1. Login to Dashboard. | Should navigate to Referral/Invite page. | No action occurs; button appears "dead". | New
2. Click 'Referral' button.
BG-04 | TC19 | Cart Removal Latency (60s Delay) | High | High | 1. Add items to cart. | Item should be removed from UI instantly. | UI takes 60 seconds to refresh/remove the item. | Open
2. Click 'Remove' in Cart page.
BG-05 | TC34 | Zip Code Accepts Non-Numeric Data | Medium | Low | 1. Proceed to Checkout. | Field should show "Invalid Zip" error. | System accepts alphabets and allows checkout. | New
2. Enter 'ABCDE' in Zip Code.
BG-06 | TC40 | Blog Page Link Broken (404) | Medium | Medium | 1. Click 'Blog' in Sidebar/Footer. | Should redirect to official Blog page. | Shows "Feature not responding" or 404 error. | Open
BG-07 | TC35 | Security Flaw: Cache Data Visible | High | Medium | 1. Logout from application. | Should redirect to Login (Auth required). | Inventory page is visible via browser cache. | Open
2. Click Browser 'Back' button.
BG-08 | TC38 | Checkout Error: System Crash | Critical | High | 1. Login with error_user. | Order should be placed successfully. | System shows "Internal Error" or freezes on Continue. | New
2. Complete Checkout info.
BG-09 | TC26 | Reset App State UI Sync Issue | Low | Low | 1. Add item. | Cart count should become 0 instantly. | Cart count stays '1' until manual page refresh. | Open
2. Menu -> Reset App State.
BG-10 | TC30 | Twitter Link Redirect Issue | Low | Low | 1. Scroll to Footer. | Should open @saucelabs Twitter. | Redirects to a broken or generic Twitter home. | New
2. Click Twitter Icon.

## Test Planing
Section | Details
Project Name | Sauce Demo (Swag Labs) E-commerce Testing
Tester Name | Manish
Date | 2026-03-24
Objective | Verify Login, Cart, and Checkout functionality.
Testing Type | Manual Testing (Black Box)
Scope | Functional, UI, and Negative Testing.
Tools | MS Excel, Chrome DevTools.
Environment | Windows 11, Chrome Browser.

## RTM
Req ID | Requirement Description | Test Case ID | Test Status | Bug ID (If any)
REQ-01 | User should be able to login with valid credentials | TC01 | PASS | -
REQ-02 | System should show error for invalid login | TC02, TC03, TC04 | PASS | -
REQ-03 | Products should be displayed with correct details | TC08, TC09, TC10 | PASS | -
REQ-04 | User should be able to sort products by price/name | TC11, TC12, TC13, TC14 | PASS | -
REQ-05 | User should be able to add/remove items from cart | TC15, TC16, TC17 | FAIL | BG-04
REQ-06 | Checkout process should collect user info & total | TC20, TC21, TC22 | PASS | -
REQ-07 | System should complete order and show success | TC23, TC24 | PASS | -
REQ-08 | Social media links should be functional | TC30, TC31, TC32 | FAIL | BG-10
REQ-09 | System should be secure (No back button access) | TC35 | FAIL | BG-07

## TestSummary
1. Project Overview
Field | Details
Project Name | Sauce Demo (Swag Labs)
Test Cycle | Cycle 01 (Initial Testing)
Tester | Manish Baghel
Status | Completed
2. Execution Summary (Numbers)
Metric | Count
Total Test Cases | 40
Passed Cases | 30
Failed Cases | 10
Blocked/Skipped | 0
3. Defect Severity Summary
Severity | Count
Critical | 1
High | 4
Medium | 3
Low | 2
Total Bugs | 10